## Time Log
Raw | Name | Hours | Description | Raw Date | Date Entered | Time Entered
Name: Robert, Email: robert@morouney.com, Hours: 3.5 | Robert Mouroney | 3.5 | Created this website! | 2016-05-07 20:43:17 -0400 | 2016-05-07 | 20:43
Name: Robert, Email: robert@morouney.com, Hours: 1.75 | Robert Mouroney | 1.75 | Edited this website and fixed some issues with this work tracker. Posted the code for this website on my git in a public repo incase the server goes down. Created a script on my server which pushes the database to git every hour. Participated in a discussion about the backend on FaceBook. | 2016-05-08 17:38:13 -0400 | 2016-05-08 | 17:38 | Enter your new rows at the bottom!
Name: Omid, Email: ghiy2250@mylaurier.ca, Hours: 2.0 | Omid Ghiyasian | 2 | Researched some web designs from apple, google, amazon, and khan academy. Reviewed the current UPOD website for things that it could be improved upon. Details can be found on http://morouney.com/CP317 | 2016-05-08 18:03:08 -0400 | 2016-05-08 | 18:03
Name: Lingxiao Qi, Email: qixx9940@mylaurier.ca, Hours: 2.0 | Lingxiao Qi | 2 | Writing analysis for MathJax | 2016-05-08 22:14:34 -0400 | 2016-05-08 | 22:14
Name: Kieran O'Driscoll, Email: oxdr1700@mylaurier.ca, Hours: 0.5 | Kieran O'Driscoll | 0.5 | Found resources for Git for those who have never used it and need to learn. 2 Interactive tutorials and a lengthy document on Git | 2016-05-09 11:16:29 -0400 | 2016-05-09 | 11:16
Name: Kyle Colle-Tripp, Email: coll5360@mylaurier.ca, Hours: 2.5 | Kyle Colle-Tripp | 2.5 | Planning/sketching front-end design | 2016-05-10 12:19:47 -0400 | 2016-05-10 | 12:19
Name: Tom West, Email: west2980@mylaurier.ca, Hours: 1.5 | Tom West | 1.5 | Set up IEEE compliant Software Requirements Specification Template for Requirements team | 2016-05-10 15:25:07 -0400 | 2016-05-10 | 15:25
Name: Robert, Email: robert@morouney.com, Hours: 0.25 | Robert Mouroney | 0.2 | fixed the work tracker. | 2016-05-13 00:21:24 -0400 | 2016-05-13 | 00:21
Name: Ryan Mak, Email: makx1280@mylaurier.ca, Hours: 3.0 | Ryan Mak | 3 | Drafted a prototype of the UPOD homepage and attended a meeting discussing various design standards | 2016-05-13 14:22:48 -0400 | 2016-05-13 | 14:22
Name: Robert Morouney, Email: robert@morouney.com, Hours: 2.25 | Robert Mouroney | 2.2 | Created Use-Case Diagram for the back-end features. Researched and wrote up the pros and cons for Ruby on Rails and Node.js as frameworks and deployment solutions. Participated in online discussions and created poll to further the framework selection process. | 2016-05-13 15:44:18 -0400 | 2016-05-13 | 15:44
Name: Omid, Email: ghiy2250@mylaurier.ca, Hours: 2.5 | Omid Ghiyasian | 2.5 | Planning/Sketching Front end Design (Group meeting) | 2016-05-13 15:49:43 -0400 | 2016-05-13 | 15:49
| Wallise Wu | 1.5 | Physics Research Content - Electromagnetism (magnets and field forces) |  | 2016-05-13 | 18:53
Name: Jeffrey Chung, Email: jeffreychung6@gmail.com, Hours: 1.0 | Jeffery Chung | 1 | Wrote in the reference RD v0.1 - UPOD Standards that is the product scope, product perspective and the intended audience. Also wrote in the product scope of reference document RD v0.1 - UPOD Web Design. | 2016-05-14 08:31:27 -0400 | 2016-05-14 | 08:31
Name: Franco, Email: wong9661@mylaurier.ca, Hours: 0.75 | Franco | 0.75 | Looked into the search function for the website | 2016-05-14 18:07:29 -0400 | 2016-05-14 | 18:07
Name: Kieran O'Driscoll, Email: oxdr1700@mylaurier.ca, Hours: 1.0 | Kieran O'Driscoll | 1 | Django framework pros and cons analysis | 2016-05-16 10:42:43 -0400 | 2016-05-16 | 10:42
Name: Kieran O'Driscoll, Email: oxdr1700@mylaurier.ca, Hours: 0.5 | Kieran O'Driscoll | 0.5 | Draft back-end requirements doc for the requirements group | 2016-05-16 10:43:21 -0400 | 2016-05-16 | 10:43
Name: Will Detlor, Email: detl8600@mylaurier.ca, Hours: 1.0 | Will Detlor | 1 | Added research for Node.js and Rails to Back End requirement document. Added in TO DO list regarding requirements for API, authentication, and URLs | 2016-05-16 11:08:54 -0400 | 2016-05-16 | 11:08
Name: Jordan, Email: viss3240@mylaurier.ca, Hours: 1.0 | Jordan Visser | 1 | Drafted requirements for animations portion of the project. | 2016-05-16 20:28:16 -0400 | 2016-05-16 | 20:28
Name: Joseph Vannelli, Email: vann7860@mylaurier.ca, Hours: 1.0 | Joseph Vannelli | 1 | Collaborated with the other members of the animation team to draft a requirements document for the animations portion of the project. | 2016-05-16 20:30:41 -0400 | 2016-05-16 | 20:30
Name: Giacinto Romano, Email: roma1150@mylaurier.ca, Hours: 1.0 | Giacinto Romano | 1 | Drafted requirements for animations portion of the project. | 2016-05-16 20:30:06 -0400 | 2016-05-16 | 20:30
Name: Kieran. O'Driscoll, Email: oxdr1700@mylaurier.ca, Hours: 1.0 | Kieran O'Driscoll | 1 | Worked on draft of requirements for back end, add more detail and expanded on some features | 2016-05-17 18:00:19 -0400 | 2016-05-17 | 18:00
Name: Tom West, Email: west2980@mylaurier.ca, Hours: 5.5 | Tom West | 5.5 | Completed functional requirements for Web Design. Can be found in General Slack Channel | 2016-05-17 18:22:24 -0400 | 2016-05-17 | 18:22
| Clive Shen | 6 | Completed description and functional requirements for Back End RD. | 2016-05-17 23:00:00 -0400 | 2016-05-17 | 23:00
Name: Mines Varu, Email: varu4300@mylaurier.ca, Hours: 2.5 | Mines Varu | 2.5 | Helped with requirements building for the front-end section, in particular naming font sizes/percentages, also wrote a couple of helpful notes about the front-end section | 2016-05-18 10:47:58 -0400 | 2016-05-18 | 10:47
Name: Jeffrey Chung, Email: jeffreychung6@gmail.com, Hours: 0.5 | Jeffery Chung | 0.5 | Worked on the rough version of references for graphics/animation | 2016-05-18 11:07:08 -0400 | 2016-05-18 | 11:07
Name: Steven Gao, Email: gaox9460@mylaurier.ca, Hours: 3.5 | Steven Gao | 3.5 | Completed the functional requirements section for Graphics/Animation of the SRS document. | 2016-05-18 22:31:40 -0400 | 2016-05-18 | 22:31
| Anders Lam | 4 | Worked on the rough draft of the requirements document for Physics Content |  | 2016-05-24 | 20.31
| Anders Lam | 3 | Updated product description section of the physics requirements document |  | 2016-05-28 | 17:30
Name: Kyle Colle-Tripp, Email: coll5360@mylaurier.ca, Hours: 3.0 | Kyle Colle-Tripp | 3 | Finishing frontend-design on paper | 2016-05-28 15:31:50 -0400 | 2016-05-28 | 15:31
Name: Ryan Mak, Email: makx1280@mylaurier.ca, Hours: 4.0 | Ryan Mak | 4 | Attended a meeting further working on Front-End design decisions and visuals. Also improved the UML diagram to reflect on these new changes. | 2016-05-28 17:48:19 -0400 | 2016-05-28 | 17:48
Name: Omid Ghiyasian, Email: ghiy2250@mylaurier.ca, Hours: 3.0 | Omid Ghiyasian | 3 | Group meeting with front end design and UML diagrams. | 2016-05-28 19:34:54 -0400 | 2016-05-28 | 19:34
Name: Kyle Colle-Tripp, Email: coll5360@mylaurier.ca, Hours: 4.0 | Kyle Colle-Tripp | 4 | Wrote header/footer for website, did some management stuff | 2016-05-29 16:06:23 -0400 | 2016-05-29 | 16:06
Name: Kyle Colle-Tripp, Email: coll5360@mylaurier.ca, Hours: 4.0 | Kyle Colle-Tripp | 4 | Wrote header/footer for website, did some management stuff | 2016-05-29 16:06:23 -0400 | 2016-05-29 | 16:06
Name: Vishrut Sutaria, Email: suta8636@mylaurier.ca, Hours: | Vishrut Sutaria | ? |  | 2016-05-29 16:39:48 -0400 | 2016-05-29 | 16:39
Name: Ryan Mak, Email: makx1280@mylaurier.ca, Hours: 2.0 | Ryan Mak | 2 | Created the homepage (landing page). | 2016-05-29 16:40:49 -0400 | 2016-05-29 | 16:40
Name: Vishrut Sutaria, Email: suta8636@mylaurier.ca, Hours: 3.75 | Vishrut Sutaria | 3.75 | created Entry page in html for vapourware | 2016-05-29 16:41:17 -0400 | 2016-05-29 | 16:41
Name: Kyle Colle-Tripp, Email: coll5360@mylaurier.ca, Hours: 1.0 | Kyle Colle-Tripp | 1 | did more work on vapourware | 2016-05-29 16:42:23 -0400 | 2016-05-29 | 16:42
Name: Roman Lipisiy, Email: lipi4200@mylaurier.ca, Hours: 3.0 | Roman Lipisiy | 3 | create about and search results html pages | 2016-05-29 17:55:39 -0400 | 2016-05-29 | 17:55
Name: Ensieh Mollazadeh, Email: moll7720@mylaurier.ca, Hours: 4.0 | Ensieh Mollazedeh | 4 | writing the code for portal page | 2016-05-29 19:58:49 -0400 | 2016-05-29 | 19:58
Name: Ensieh Mollazadeh, Email: moll7720@mylaurier.ca, Hours: 3.0 | Ensieh Mollazedeh | 3 | planning the basic design of the web pages. | 2016-05-29 20:02:26 -0400 | 2016-05-29 | 20:02
Name: Qamar Farooq, Email: ch.farooq.qamar@hotmail.com, Hours: 6.0 | Qamar Farooq | 6 | Coded the pages for administer. | 2016-05-30 00:24:50 -0400 | 2016-05-30 | 00:24
Name: Qamar Farooq, Email: ch.farooq.qamar@hotmail.com, Hours: 3.0 | Qamar Farooq | 3 | designed admin and moderator pages | 2016-05-30 00:24:19 -0400 | 2016-05-30 | 00:24
Name: Ryan Mak, Email: makx1280@mylaurier.ca, Hours: 1.25 | Ryan Mak | 1.25 | Further worked on homepage; fixed issues with homepage design | 2016-05-30 01:18:49 -0400 | 2016-05-30 | 01:18
Name: Vikrant Sharma, Email: shar6770@mylaurier.ca, Hours: 3.0 | Vikrant Sharma | 3 | First design team in person meeting, we discussed and drew out layouts of all the webpages | 2016-05-30 01:37:55 -0400 | 2016-05-30 | 01:37
Name: Vikrant Sharma, Email: shar6770@mylaurier.ca, Hours: 4.0 | Vikrant Sharma | 4 | Answered the requirement teams questions and created a document to answer the questions. | 2016-05-30 01:39:04 -0400 | 2016-05-30 | 01:39
Name: Vikrant Sharma, Email: shar6770@mylaurier.ca, Hours: 3.0 | Vikrant Sharma | 3 | Fixed the dynamic loading issue. The main issue was the javascript was missing $(document).ready(main); The other issue was bootstrap was not loaded in properly, so I used CDN links instead. | 2016-05-30 01:42:14 -0400 | 2016-05-30 | 01:42
Name: Ryan Mak, Email: makx1280@mylaurier.ca, Hours: 1.25 | Ryan Mak | 1.2 | Updated UML diagram to include new files and attributes | 2016-05-30 13:17:43 -0400 | 2016-05-30 | 13:17
Name: Ryan Mak, Email: makx1280@mylaurier.ca, Hours: 2.5 | Ryan Mak | 2.5 | Started on physics research. Found Optics notes (PC237) and started writing down important info. | 2016-05-30 16:31:56 -0400 | 2016-05-30 | 16:31
Name: Aman Kumar, Email: kuma6620@mylaurier.ca, Hours: 4.0 | Aman Kumar | 4 | Completed first draft of Classical Mechanics research for the physics content that will be added to the UPOD site. | 2016-05-31 19:32:46 -0400 | 2016-05-31 | 19:32
Name: Kevin Mehta, Email: meht0360@mylaurier.ca, Hours: 3.0 | Kevin Mehta | 3 | Completed part 1 of Fundamentals research. Included some animation diagrams and concepts. | 2016-05-31 20:47:56 -0400 | 2016-05-31 | 20:47
| Wallise Wu | 3 | Completed all parts of the physics electromagnets physics research and uploaded to repository |  | 2016-05-31 | 0.94653
| Clive Shen | 7 | Updated product persepctive and function, as well as actors and use cases for Back End RD. | 2016-05-31 23:48:23 -0400 | 2016-05-31 | 23:48
Name: Ryan Mak, Email: makx1280@mylaurier.ca, Hours: 2.0 | Ryan Mak | 2 | Updated webpages to have links to other pages and touched up on physics research/ note formatting | 2016-06-01 20:20:06 -0400 | 2016-06-01 | 20:20
Name: Omid Ghiyasian, Email: ghiy2250@mylaurier.ca, Hours: 8.0 | Omid Ghiyasian | 8 | Research/Guide on Ruby for front end designer use. | 2016-06-04 17:08:14 -0400 | 2016-06-04 | 17:08
Name: Ryan Mak, Email: makx1280@mylaurier.ca, Hours: 0.75 | Ryan Mak | 0.75 | Added the forgot password page and linked the login page to this page, | 2016-06-06 14:02:19 -0400 | 2016-06-06 | 14:02
Name: Brian Oh, Email: ohxx5810@mylaurier.ca, Hours: 3.0 | Brian Oh | 3 | Discussing the SRS with SQA team and evaluating, and providing feedback for the groups in regards to Requirement documents. | 2016-06-11 19:29:48 -0400 | 2016-06-11 | 19:29
Name: Omid Ghiyasian, Email: ghiy2250@mylaurier.ca, Hours: 3.0 | Omid Ghiyasian | 3 | Reviewed the SRS with the SQA team. (Group meeting) | 2016-06-12 01:32:07 -0400 | 2016-06-12 | 01:32
Name: Omid Ghiyasian, Email: ghiy2250@mylaurier.ca, Hours: 8.0 | Omid Ghiyasian | 8 | Studied on requirements and analysis in order to refine the SRS documents to create a template for the requirements team. Discussed details with SQA team. Resources: Object Oriented Software Engineering by Stephen R. Schach and IEEE template for an SRS. | 2016-06-12 01:34:34 -0400 | 2016-06-12 | 01:34
| Michael Roher | 4.5 | Created vagrant box and instructions on how to use it |  | 2016-06-12 | 0.41389
Name: Brian Oh, Email: ohxx5810@mylaurier.ca, Hours: 2.0 | Brian Oh | 2 | Created original prototype of homepage, drop-down menu, alternate page from a sample link. | 2016-06-12 11:54:51 -0400 | 2016-06-12 | 11:54
Name: Jordan Visser, Email: viss3240@mylaurier.ca, Hours: 2.0 | Jordan Visser | 2 | Conducted research on Javascript Libraries Vivus and Bonsai for SVG animations. | 2016-06-12 14:21:15 -0400 | 2016-06-12 | 14:21
Name: Giacinto Romano, Email: roma1150@mylaurier.ca, Hours: 1.5 | Giacinto Romano | 1.5 | Conducted research on which Library to use for SVG animation. Specifically the Velocity.js library | 2016-06-12 22:47:30 -0400 | 2016-06-12 | 22:47
Name: Omid Ghiyasian, Email: ghiy2250@mylaurier.ca, Hours: 4.0 | Omid Ghiyasian | 4 | Made HTML versions of the requirement document for the Web Design and the Template file for SRS documents. Files can be found on Github | 2016-06-13 03:52:58 -0400 | 2016-06-13 | 03:52
Name: Kieran O'Driscoll, Email: oxdr1700@mylaurier.ca, Hours: 2.0 | Kieran O'Driscoll | 2 | Setting up backend environment locally and learning ruby on rails. | 2016-06-13 11:23:12 -0400 | 2016-06-13 | 11:23
Name: Vishrut Sutaria, Email: suta8636@mylaurier.ca, Hours: 4.5 | Vishrut Sutaria | 4.5 | Helped omid with Research for Guide on Ruby for front end designer use. | 2016-06-14 00:23:48 -0400 | 2016-06-14 | 00:23
Name: Omid Ghiyasian, Email: ghiy2250@mylaurier.ca, Hours: 1.5 | Omid Ghiyasian | 1.5 | Updated the HTML version of the SRS Template for individual groups. Follow up from 2016-06-13 | 2016-06-14 00:32:57 -0400 | 2016-06-14 | 00:32
Name: Pillip Lee, Email: leex6220@mylaurier.ca, Hours: 2.0 | Pillip Lee | 2 | - Updated/Edited the Statistical Mechanics content of the Physics Research Group | 2016-06-15 00:33:58 -0400 | 2016-06-15 | 00:33
Name: Joseph Vannelli, Email: vann7860@mylaurier.ca, Hours: 1.0 | Joseph Vannelli | 1 | Created a document with the pros and cons for the Raphael JS library | 2016-06-15 11:49:11 -0400 | 2016-06-15 | 11:49
Name: Joseph Vannelli, Email: vann7860@mylaurier.ca, Hours: 1.0 | Joseph Vannelli | 1 | Created a document with the pros and cons for the Snap library for SVG animations | 2016-06-15 11:51:14 -0400 | 2016-06-15 | 11:51
Name: Will Detlor, Email: detl8600@mylaurier.ca, Hours: 7.0 | Will Detlor | 7 | Setup Ruby on Rails app and environment. Go through tutorial to learn tools needed for backend development | 2016-06-15 20:18:53 -0400 | 2016-06-15 | 20:18
Name: Will Detlor, Email: detl8600@mylaurier.ca, Hours: 3.0 | Will Detlor | 3 | -Meeting with backend group to discuss categories/routing and then meeting with Dr. Brown | 2016-06-15 20:18:16 -0400 | 2016-06-15 | 20:18
Name: Will Detlor, Email: detl8600@mylaurier.ca, Hours: 1.0 | Will Detlor | 1 | Time spent answering emails/slack | 2016-06-15 20:19:24 -0400 | 2016-06-15 | 20:19
Name: Will Detlor, Email: detl8600@mylaurier.ca, Hours: 1.0 | Will Detlor | 1 | -Cloning UPOD scaffolding branch and getting it working on local environment (troubleshooting issues) | 2016-06-16 20:53:51 -0400 | 2016-06-16 | 20:53
Name: Brian Oh, Email: ohxx5810@mylaurier.ca, Hours: 1.5 | Brian Oh | 1.5 | Created 'More' Drop-down menu in homepage with links. | 2016-06-16 23:59:17 -0400 | 2016-06-16 | 23:59
Name: Brian Oh, Email: ohxx5810@mylaurier.ca, Hours: 0.5 | Brian Oh | 0.5 | Reviewed re-submitted Physics SQA requirement and documented for a second edit with instructions for each | 2016-06-17 02:53:23 -0400 | 2016-06-17 | 02:53
Name: Roman Lipisiy, Email: lipi4200@mylaurier.ca, Hours: 3.0 | Roman Lipisiy | 3 | Merge all style sheets together for frontend | 2016-06-17 11:22:30 -0400 | 2016-06-17 | 11:22
Name: wu wen, Email: wenx7330@mylaurier.ca, Hours: 1.25 | Wu Wen | 1.25 | Created a document with the pros and cons for the SVG.JS library | 2016-06-17 12:39:37 -0400 | 2016-06-17 | 12:39
Name: Pillip Lee, Email: leex6220@mylaurier.ca, Hours: 1.5 | Pillip Lee | 1.5 | Started working on Physics Content Tags" for the Database team." | 2016-06-17 22:47:54 -0400 | 2016-06-17 | 22:47
| Clive Shen | 6 | Edited the Back End RD based on the new template, and converted it into HTML format. | 2016-06-17 22:50:23 -0400 | 2016-06-17 | 22:50
Name: Brian Oh, Email: ohxx5810@mylaurier.ca, Hours: 4.0 | Brian Oh | 4 | Created a compete Template with into HTML with working Table of contents for Requirements groups to fill out. Also converted submitted Physics Requirements document into proper html formatting. | 2016-06-18 11:31:35 -0400 | 2016-06-18 | 11:31
| Omid Ghiyasian | 1 | Front End Meeting with David Brown 17/06 12pm | 2016-06-18 11:32:20 -0400 | 2016-06-18 | 0.48125
Name: Tudor Bertiean, Email: bert8270@mylaurier.ca, Hours: 3.0 | Tudor Bertiean | 3 | Started admin page mock up, basic template, started on the action side-bar. | 2016-06-18 17:52:21 -0400 | 2016-06-18 | 17:52
Name: Tudor Bertiean, Email: bert8270@mylaurier.ca, Hours: 1.0 | Tudor Bertiean | 1 | Refactoring the side-bar in admin page. 06/01 | 2016-06-18 17:53:54 -0400 | 2016-06-18 | 17:53
Name: Tudor Bertiean, Email: bert8270@mylaurier.ca, Hours: 1.0 | Tudor Bertiean | 1 | Refactoring all html files for tabs and changed variable names for name-name style. 05/31 | 2016-06-18 17:53:38 -0400 | 2016-06-18 | 17:53
Name: Tudor Bertiean, Email: bert8270@mylaurier.ca, Hours: 2.0 | Tudor Bertiean | 2 | Styling of the action side-bar on admin page. 05/30 | 2016-06-18 17:53:13 -0400 | 2016-06-18 | 17:53
| Michael Roher | 2 | Prepared for lecture on Ruby on Rails and gave lecture |  | 2016-06-20 | 0.375
| Michael Roher | 4 | Developed the initial models for the articles and established the associations between them (Articles, ArticleBlock, Constant, ArticleTextBlock, ArticleLinkBlock, ArticleConstantBlock, ArticleEquationBlock, etc.) |  | 2016-06-20 | 0.375
Name: Ryan Mak, Email: makx1280@mylaurier.ca, Hours: 6.0 | Ryan Mak | 6 | Redesigned the push menu using CSS only, designed a template for future use, and updated all previous pages to incorporate the push menu. | 2016-06-20 18:53:51 -0400 | 2016-06-20 | 18:53
| Michael Roher | 0.5 | Transferred Time Log to Spreadsheet |  | 2016-06-21 | 0.59375
| Delia Lazarescu | 2 | Created admin login page |  | 2016-05-28 | 0.58333
| Delia Lazarescu | 0.5 | Helped solve div/spacing problem on admin page |  | 2016-05-28 | 0.66667
| Delia Lazarescu | 2 | Fixed login page css/design, header and footer |  | 2016-06-01 | 0.75
| Delia Lazarescu | 1 | Group meeting to begin sketching front end design |  | 2016-05-10 | 0.79167
| Michael Roher | 0.75 | Created a list of to-dos for the article group of the back-end team with varying difficulty levels and comments on the best approach |  | 2016-06-21 | 0.60347
| David Ka Wai Chan | 5 | Designed Database Scehma |  | 2016-06-21
| David Ka Wai Chan | 2 | Reviewed Graphics SQA, provide requirement person feedbacks |  | 2016-06-21
| David Ka Wai Chan | 0.5 | Set up Rails on machine |  | 2016-06-21
| Wallise Wu | 2.5 | Created content template for Physics research team |  | 2016-06-21 | 0.7625
| Wallise Wu | 1 | Added tags to electromagnets section and installed Rails on machine |  | 2016-06-21 | 0.76319
| Michael Roher | 0.5 | Setting up the article model to store the different blocks in the correct order and added an interface to interact with them much more easily |  | 2016-06-21 | 0.92361
| Jeffery Chung | 3 | Worked on the Graphics/animation requirements on Word and HTML |  | 2016-06-19
| Anders Lam | 3.5 | Edited the physics content requirements based on new template and HTML |  | 2016-06-19 | 0.71875
| Kieran O'Driscoll | 1 | Validations for the database under the models folder |  | 2016-06-22 | 0.81181
| Kieran O'Driscoll | 1 | Created Analysis Document Templated |  | 2016-06-23 | 0.575
| Tudor Bertiean | 1 | Team meeting for admin page redesigns |  | 2016-06-23 | 0.69167
| Ensieh Mollazedeh | 2 | research to make a draggable image for concave mirror |  | 2016-06-22 | 0.72917
| Ensieh Mollazedeh | 4 | draw the concave mirror in Inkscape |  | 2016-06-17
| Ensieh Mollazedeh | 4 | working on concave mirror animation |  | 2016-06-20
| Ensieh Mollazedeh | 2 | making progress in dragging the object an moving the image in concave mirror |  | 2016-06-23 | 0.79167
| Wallise Wu | 0.75 | Coordinated between front end/back end/diagrams team on content integration |  | 2016-06-23 | 0.91319
| Muttahir Zia | 3 | SQA Review of Back End And Front End Requirements, committed to UPOD |  | 2016-06-24 | 0.50069
| Ensieh Mollazedeh | 3 | Work on concave mirror and create a resistor shape in shapes.html in the github |  | 2016-06-24 | 0.55833
| Anders Lam | 3 | Worked on updating Physics RD on HTML to fit the standard template |  | 2016-06-24 | 0.96806
| Brian Oh | 1.5 | Revised formatting and errors in Physics RD. Fixed Table of Contents and working links to match specific indentation. Edits and suggestions sent to SQA lead of Physics for further revision. |  | 2016-06-25 | 0.76111
| Ensieh Mollazedeh | 2 | research svg translation and scaling and work on the image in concave mirror. |  | 2016-06-25 | 0.84097
| Omid Ghiyasian | 4 | Group meeting over discord with Front end discussing analysis of the requirements and specific features that the front end would provide. Some SQA feedback on the SRS documents. (View UPOD RD - Web Design (Edited).docx commited on Jun 25, 2016 for reference). |  | 2016-06-25 | 21:06
| Eric Jiang | 3 | Readover and Edit Physics requirements document |  | 2016-06-25 | 0.92847
| Brian Oh | 1.5 | Revised formatting and errors in Back End RD. Fixed Table of Contents and working links to match specific indentation. Edits and suggestions sent to SQA lead of Back End for further revision. |  | 2016-06-25 | 0.97917
| Brian Oh | 0.5 | Revised Graphics RD. Edits and suggestions sent to SQA lead of Back End for further revision. |  | 2016-06-25 | 0.99653
| Michael Roher | 5 | Integrating Sir Trevor - block editor to create posts. |  | 2016-06-26 | 0.58889
| Ensieh Mollazedeh | 3 | fix the problem with image not moving on a staright line when using scale. Having done a lot of research to do that. Also apply the physics formula on the movement of the object and image. |  | 2016-06-26 | 0.70278
| Anders Lam | 1.5 | Revised Physics HTML RD according to SQA Review and changes required |  | 2016-06-26 | 0.70208
| Steven Swartz | 0.5 | Changed database ERD by fixing table relationships and adding user permissions to the UserGroups table |  | 2016-05-29
| Steven Swartz | 0.5 | Created preliminary requirements and functions for the User Management Portal |  | 2016-05-17
| Steven Swartz | 0.5 | Recorded pros/cons of using PHP and its popular frameworks (Symfony, PHP/Slim) |  | 2016-05-17
| Steven Swartz | 0.25 | Specified data accessility requirements for administrators, modertors and users |  | 2016-06-16
| Steven Swartz | 2 | Designed a format for creating and presenting UML diagrams with StarUML for the analysis stage |  | 2016-06-26 | 0.85556
| Steven Swartz | 1 | Created preliminary class diagram for the article classes and added relationships with other packages |  | 2016-06-26 | 0.85556
| Kieran O'Driscoll | 1.5 | Contributed to Analysis Document |  | 2016-06-26 | 0.95625
| Pillip Lee | 1 | Restructured the Stats. Physics Content to align it with the new format |  | 2016-06-26 | 0.98403
| Jeffrey Chung | 1 | Updated graphics requirement document and html due to comments |  | 2016-06-27 | 0.23958
| David Ka Wai Chan | 1 | Created Category UML, merged to git |  | 2016-06-27
| David Ka Wai Chan | 0.25 | Added SQA comments for Graphics |  | 2016-06-27
| Derek Cruise | 0.25 | Updated Back-end UML Diagram |  | 2016-06-27
| Vishrut Sutaria | 0.5 | redesigned the categories page by changing positions of chategories in the grids |  | 2016-06-27 | 0.67847
| Vishrut Sutaria | 0.5 | added jumbotron inside the column div to make each category and its content look separate from the other categories, and all the sub categories links are linked to the old categories page which is now called subcategories page |  | 2016-06-27 | 0.68056
| Vishrut Sutaria | 0.5 | read this website - http://getbootstrap.com/components/ to see if there is something else beside jumbotron |  | 2016-06-27 | 0.68264
| Aman Kumar | 0.5 | Prepared list of all diagrams (both static and interactive) for Classical Mechanics for animation team |  | 2016-06-27 | 0.73681
| Aman Kumar | 2.5 | Compiled a list of interactive diagrams for Fundamentals. Wrote the description for how two diagrams will work; Elastic collision and potential energy. |  | 2016-06-27 | 0.73819
| Jordan Visser | 3 | Created the projectile motion SVG diagram. Still needs projectile motion off a cliff, animation, and allow for user input | 2016-05-16 20:28:16 -0400 | 2016-06-27 | 20:28
| Joseph Vannelli | 3.5 | Created a free body SVG diagram on Newton's laws of motion and did research on how to create buttons in the diagram to enable interactivity |  | 2016-06-27 | 0.81875
| Aman Kumar | 3.5 | Created an extensive hierarchy and list of tags in microsoft visio for 4/6 of the physics topics and all of their associated subtopics. The following concepts were covered in the hierarchy: Fundamentals, Classical Mechanics, Statistical Mechanics, Electricity and Magnetism. Topics Remaning: Optics and Quantum Mechanics. The diagram was also exported to powerpoint for easy viewing. |  | 2016-06-27 | 0.88542
| Kieran O'Driscoll | 0.5 | Contributed to Analysis Document |  | 2016-06-27 | 0.91667
| Kieran O'Driscoll | 1.5 | Rspec and Shoulda Matcher testing |  | 2016-06-27 | 0.6875
| Tom West | 2 | 06/12/16 - Met with Front End to update Req Doc template + began to redo Front End RD |  | 2016-06-27 | 0.97917
| Tom West | 3 | 06/15/16 - Updated Front End RD |  | 2016-06-28 | 1.0208
| Tom West | 4 | 06/16/16 - Completed Initial Draft of redone Front End RD |  | 2016-06-29 | 1.0625
| Tom West | 3.5 | 06/19/16 - Made updates based on SQA feedback to Front End RD |  | 2016-06-30 | 1.1042
| Tom West | 2 | 06/22/16 - Made updates based on second round of SQA feedback to Front End RD |  | 2016-07-01 | 1.1458
| Roman Lipisiy | 5 | 07/01/16 - Migrated vapourware files to ruby on rails scaffolding |  | 2016-07-01 | 0.15625